SiteChat — Assessment 2 Industry Project Report

Week 6 Deliverables: Executive Summary, Introduction & Project Planning

| Field | Details |
| --- | --- |
| Project | SiteChat — real-time site communication platform for Crennotech Pty Ltd (CleanTasker) |
| Assessment | ICT942 Assessment 2 — Industry Project Report (40% — 20% report + 20% presentation) |
| Deliverable date | Week 6 (by Sunday 30 August 2026) |
| Prepared by | Amrit Dahal (PM), Madhab Poudel (BA), Subham Giri (Tech Lead), Sujit Budhathoki (QA & Documentation) |
| Supervisor | Dr Ashraf Uddin (client mentor: Kiran Vilasagaram, Crennotech) |

# Executive Summary

Crennotech Pty Ltd's CleanTasker platform coordinates commercial cleaning operations across Australia and New Zealand, but cleaners, supervisors, managers and clients currently rely on ad-hoc phone calls and SMS to communicate at the site level, separate from the operational data already held in CleanTasker. This fragmentation causes missed task updates, delayed responses to site issues, and no auditable record of site-level communication.

SiteChat is proposed as a real-time, site-scoped communication platform built on React (TypeScript), Flutter and Firebase, integrated with existing CleanTasker APIs via an Azure-hosted backend. Each client site has its own isolated, secured chat room combining human messages with system-generated operational alerts, so cleaners, supervisors, managers and clients see a single, auditable communication trail per site.

This report builds on the Semester 1 analysis and design (project charter, stakeholder analysis, requirements specification, architecture and risk register) and extends it into a full industry project report: an updated business case, a technology landscape analysis, a refined solution design and cost model, and a working proof of concept demonstrating real-time, access-controlled messaging.

The proof of concept, to be evaluated against measured KPIs in Week 8, is expected to demonstrate that Firestore-based multi-tenant isolation and sub-2-second message delivery are both technically achievable within the team's skill set and budget.

We recommend Crennotech proceed to a funded pilot of SiteChat across a limited set of sites in Semester 2 following successful completion of this proof of concept, with Firestore security-rule testing treated as a gating requirement before any further build work.

# 1. Introduction

## 1.1 Business Context & Problem Statement

Crennotech Pty Ltd is a Brisbane-based technology company behind CleanTasker, a management platform used by commercial cleaning agencies across Australia and New Zealand to schedule jobs, manage staff and administer contracts. Site-level communication — between cleaners, supervisors, managers and clients — currently happens outside CleanTasker, through personal phone calls, SMS and informal messaging apps.

This creates three quantifiable problems: (1) operational alerts such as overdue tasks or failed inspections are not reliably seen by the right person, since there is no shared channel tied to the relevant site; (2) there is no audit trail of site-level communication, which matters when a client disputes whether an issue was raised or actioned; and (3) onboarding a new site currently requires staff to set up ad-hoc phone/SMS groups manually, adding delay before a site becomes fully operational.

Because site communication may reference client-confidential operational data (schedules, access details, incident reports), any solution must enforce strict per-site data isolation and control access by role — the same cybersecurity lens applied throughout Semester 1.

## 1.2 Goals, Objectives & Success Criteria

- O1 [Design]: By Week 7, finalise the SiteChat solution architecture, technology stack, and cost model, peer-reviewed by the team and approved by the supervisor.

- O2 [Analyse]: By Week 7, complete a technology and market survey of at least 3–4 comparable site-communication tools, with a gap analysis linking each gap to the proposed solution.

- O3 [Build]: By Week 8, implement a working proof of concept demonstrating real-time, access-controlled messaging within a single Firestore-secured site room, using synthetic data only.

- O4 [Evaluate]: By Week 8, measure PoC performance against at least 2 KPIs — message delivery latency and Firestore security-rule test pass rate.

Success criteria:

- PoC delivers messages to all connected participants within 2 seconds under normal load.

- 100% of automated Firestore security-rule tests pass, with no cross-site data access possible.

- Cost model validated against real Firebase and Azure pricing calculators, not estimated figures.

## 1.3 Project Scope

### In Scope

- Technology and market landscape analysis for site-level communication tools.

- Refinement of the SiteChat architecture, Firestore data model and security rules from Semester 1.

- A working proof of concept for one core feature: real-time, site-scoped messaging with access control.

- Cost-benefit analysis and feasibility study for a limited-site pilot deployment.

### Out of Scope

- Full production deployment of SiteChat (proof of concept only).

- Integration with real, live CleanTasker data or production client sites.

- Attachments, notifications and system-message features beyond the core messaging PoC (documented as future work).

### Assumptions

- The team retains access to a Firebase Spark/Blaze development project and Azure trial credit for the PoC.

- Team members retain baseline proficiency in React, Flutter and Firebase from Semester 1 SRS work.

### Constraints

- Three-week timeline (Weeks 6–8) to complete the full Assessment 2 report and PoC.

- PoC data must be synthetic or de-identified — no real CleanTasker client data.

- Must comply with the Privacy Act 1988 and Crennotech's existing confidentiality obligations.

# 2. Project Planning

## 2.1 Project Charter

| Field | Details |
| --- | --- |
| Project title | SiteChat — Real-Time Site Communication Platform for CleanTasker |
| Sponsor | Crennotech Pty Ltd (client mentor: Kiran Vilasagaram) |
| Project Manager | Amrit Dahal |
| Duration | Weeks 6–8 (24 August – 13 September 2026) |
| Budget | Firebase Spark/Blaze development tier + Azure trial credit; no capital budget for Semester 2 pilot at this stage |
| Scope summary | Landscape analysis, solution design refinement, cost model, and a working PoC for real-time site-scoped messaging |
| Key stakeholders | Crennotech sponsor, CleanTasker Dev/API team, cleaning supervisors and staff, commercial clients, CIHE project team |
| Acceptance criteria | PoC meets the KPIs in Section 1.2; report meets the Assessment 2 word count, structure and referencing requirements |
| Delegated authority | Project Manager may re-baseline the Week 6–8 schedule in Jira on unresolved supervisor escalation |

## 2.2 Project Roadmap

The roadmap follows the three-week Assessment 2 window: Week 6 (24–30 Aug) covers the business case and planning artefacts in this document; Week 7 (31 Aug–6 Sept) covers the landscape analysis, solution design and PoC start; Week 8 (7–13 Sept) covers the PoC build, evaluation, and final report compilation. The critical path runs through the PoC build in Week 8: any delay to the Week 7 PoC scaffold directly threatens the Week 8 KPI evaluation and final submission, so the team's contingency is to fix the PoC scope to a single feature (site-scoped messaging) at Week 6 kick-off rather than expanding it later. Full task-level dates are tracked in the accompanying Jira & GitHub Schedule document.

## 2.3 Team Roles & RACI Matrix

| Deliverable | Amrit (PM) | Madhab (BA) | Subham (Tech) | Sujit (QA/Doc) |
| --- | --- | --- | --- | --- |
| Industry Analysis & Landscape Report | A | R | C | I |
| Architecture Diagram | C | I | A/R | R |
| PoC Implementation | I | C | A/R | R |
| Cost Model & Feasibility Study | C | A | R | R |
| Final Report | A | R | R | R |
| Presentation | R | R | R | A/R |

A = Accountable, R = Responsible, C = Consulted, I = Informed. Each deliverable has exactly one Accountable owner.

## 2.4 Risk Register

| ID | Risk Description | L | I | Score | Rating | Response Strategy | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Dataset access for PoC delayed or restricted | 2 | 4 | 8 | Medium | Mitigate: use synthetic/de-identified data from Week 6 onward; no dependency on real CleanTasker data | Subham Giri |
| R02 | Team member unavailable mid-project (illness, work conflict) | 2 | 4 | 8 | Medium | Mitigate: document all work in shared repo; cross-train on critical Jira tasks each sprint | Amrit Dahal |
| R03 | Firebase/Azure cost overrun during PoC testing | 2 | 3 | 6 | Medium | Mitigate: set billing alerts at 80% of budget; use free-tier Spark plan for development | Subham Giri |
| R04 | Firestore security rules misconfigured, allowing cross-site data access | 2 | 5 | 10 | High | Avoid: peer-review all security rules; automated rule tests before each PoC push | Subham Giri |
| R05 | Assessment 2 word count / structure non-compliance | 2 | 3 | 6 | Medium | Mitigate: track word count weekly against the rubric; QA lead reviews structure each week | Sujit Budhathoki |
| R06 | Insufficient reference mix (too academic or too informal) | 2 | 3 | 6 | Medium | Mitigate: track reference mix (industry/vendor/academic/government) from Week 6 onward | Madhab Poudel |
| R07 | PoC scope creep delays core feature completion | 3 | 4 | 12 | High | Mitigate: fix PoC scope to one feature (real-time messaging in one site room) at Week 6 kick-off; defer extras | Amrit Dahal |
| R08 | Further client/brief changes affecting Assessment 2 scope | 2 | 4 | 8 | Medium | Mitigate: maintain change-log in Jira; re-baseline objectives and timeline promptly if scope changes | Amrit Dahal |

## 2.5 Feasibility Study

### Technical Feasibility

React, Flutter and Firebase (Firestore, Cloud Functions, Cloud Messaging) remain mature, well-documented technologies within the team's existing skill set from the Semester 1 SRS work. The main technical risk is Firestore security-rule correctness, addressed by R04 and R07 above.

### Operational Feasibility

User acceptance is expected to be favourable given the direct link to familiar CleanTasker task data, contingent on a simple onboarding walkthrough for cleaning staff and supervisors.

### Economic Feasibility

Firebase's Blaze plan is billed per Firestore read/write, Storage volume and Cloud Messaging usage rather than a licence fee; Azure hosting is similarly consumption-based. At pilot scale, combined costs are expected in the low hundreds of AUD per month, to be confirmed against real pricing calculators in Week 7's cost model (Section 4.3 of the final report).

### Legal & Regulatory Feasibility

The solution must comply with the Privacy Act 1988, including data-residency considerations, since Firebase/Google Cloud may store data outside Australia. No payment data is processed by SiteChat.