# Week 7  Risk Register

# Risk Register — Week 7

SiteChat / CleanTasker Project

| ID | Risk | Likelihood | Impact | Mitigation | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Firebase vendor lock-in limits future flexibility | Medium | Medium | Documented Supabase as a viable migration path in Technology & Market Survey; kept data model (site-scoped, timestamped) portable | Amrit | Open |
| R2 | Firestore cost scales non-linearly if message volume grows beyond MVP estimates | Low (at current scale) | Medium | Cost model includes a sensitivity note; re-costing planned if usage exceeds ~500 msgs/site/day or 50+ sites | Sujit | Open |
| R3 | Push notification delivery delays/failures on physical test devices | Medium | High (affects PoC demo credibility) | Test FCM delivery early in Week 8 (Wed), not left to final demo day | Sujit | Open |
| R4 | Firestore security rules misconfigured, exposing cross-site data | Medium | High (data privacy/compliance) | Security rules written and tested alongside schema setup in Week 8 (Mon), not deferred | Subham | Open |
| R5 | Tight Weeks 7–8 timeline leaves no buffer if a core feature (chat or notifications) slips | Medium | High | Manager dashboard (gap G6) explicitly descoped to stretch-goal to protect core PoC delivery | Amrit | Mitigated |
| R6 | Team member unavailability during PoC build week affects sprint velocity | Low | Medium | Daily push cadence and clear task ownership (see sprint plan) allow early detection of slippage | Amrit | Open |
| R7 | Manual/placeholder pricing figures in cost model not replaced with real calculator output before submission | Medium | Medium | Flagged explicitly with [TBC] markers in cost-model.md; action item assigned before final submission | Sujit | Open |

## Risk Rating Key

- Likelihood/Impact: Low / Medium / High

- Status: Open (active, monitored) / Mitigated (control in place, residual risk low) / Closed (no longer relevant)

## Notes

This register will be reviewed again during Epic 8 (Week 8) evaluation, with any new PoC-build risks (e.g. integration bugs, test device availability) added as they are identified.